## summary
bacc - diary
date | begin | end | time | activity | remarks
14.11.17 | 13:00 | 13:45 | 0:45 | -search for resources (papers, books)
15.11.17 | 12:00 | 14:30 | 2:30 | -search for resources (papers, books) -comparision of image processing libaries (Aforge, OpenCV, EMGU) -installing EMGU
17.09.18 | 11:00 | 16:30 | 5:30 | - basic framework / program sceletton
18.09. 18 | 15:00 | 16:30 | 1:30 | - basic framework / program sceletton
19.09.18 | 11:30 | 16:00 | 4:30 | - basic framework / program sceletton
22.09.18 | 14:00 | 16:00 | 2:00 | - basic framework / program sceletton
24.09.18 | 11:00 | 16:00 | 5:00 | -first tests with SURF detector -further GUI work
25.09.18 | 10:00 | 17:00 | 7:00 | -face detection tests
27.09.18 | 10:30 | 14:00 | 3:30 | -Thread issues, events, delegates
30.09.18 | 12:00 | 15:30 | 3:30 | -CascadeClassifier
19.10.18 | 11:30 | 17:00 | 5:30 | -App-Resources (GUI Design) -Preperations of Input Options
20.10.18 | 13:00 | 18:00 | 5:00 | -App-Resources (GUI Design) -WMI for list of available cameras | massive timesink on custom styles and templates reading up + tutorials
21.10.18 | 13:30 | 18:00 | 4:30 | -App-Resources (GUI Design) -WMI for list of available cameras
25. 10.18 | 13:00 | 14:30 | 1:30 | -Issues with WMI
26. 10.18 | 18:30 | 20:00 | 1:30 | -Issues with WMI
30.10.18 | 16:00 | 18:15 | 2:15 | -Cascasde-Classifier Options and refactoring
31.10.18 | 11:00 | 18:00 | 7:00 | -Cascasde-Classifier Options and refactoring
01.11.18 | 17:00 | 18:30 | 1:30 | -Add Point angle calculation
0:00
0:00
0:00
0:00
0:00
total time |  |  | 64:30